## Report
Michael Warren | [10 empty] | Last Report Date | Report as of
Task | Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours |  |  | 2014-04-02 22:27 | 2014-04-09 21:05
|  | Proposed | Modified | Actual | Proposed | Modified | Actual | Proposed | Modified | Actual
Preliminary Research/Proposal | Completed | 2014-03-06 |  | 2014-03-06 | 2014-03-13 |  | 2014-03-12 | 12 |  | 14.165
Research | In Progress | 2014-03-13 |  | 2014-03-12 | 2014-03-31 |  |  | 30 |  | 26.8042
Requirements | Completed | 2014-03-31 |  | 2014-03-15 | 2014-04-04 |  | 2014-03-26 | 6 |  | 3.7972
Design | In Progress | 2014-04-04 |  | 2014-03-26 | 2014-04-11 |  | 2014-04-09 | 12 |  | 8.2722
Math Unit Test and code | In Progress | 2014-04-11 |  | 2014-04-01 | 2014-04-24 |  |  | 18 |  | 3.395
Sequential Ray Tracer Tests and code | In Progress | 2014-04-24 |  | 2014-04-01 | 2014-05-05 |  |  | 18 |  | 5.5856
Parallel Ray Tracer Code | Not Started | 2014-05-05 |  |  | 2014-05-15 |  |  | 18 |  | 0
Cluster Ray Tracer Code | Not Started | 2014-05-15 |  |  | 2014-06-09 |  |  | 42 |  | 0
Total Hours | --- | --- | --- | --- | --- | --- | --- | 156 |  | 62.0192
Accomplishments: Finished initial design (few tweaks may be made). Found some math stuff to test. General Confrence was awesome. Planned for this Saturday off in initial estimates. Started to be allowed to let baby sleep at night.
Problems: Baby not letting me or my wife sleep as much as we want every other day in the week. Going out of town this weekend. (but that should not be bad).
Changes in Scope, Schedule, and Cost:
Confessional
Actual hours since last update: | 10.3956
Total anticipated actual hours: | 156
Behind Schedule (behind 1 hour)
Will try to catch up on some time lost this weekend since I planned to take the whole weekend off any ways.
Scripture " 15 For behold, we are in bondage to the [senior project] and are taxed with a tax which is grievous to be borne..." - Mosiah 7:15 "Even the youths shall faint and be weary, and the young men shall utterly fall: " Isaiah 40:30

## Time
Preliminary Research/Proposal | 2014-03-05 | 2014-03-05 02:00 | 2
Preliminary Research/Proposal | 2014-03-06 | 2014-03-06 03:00 | 3
Preliminary Research/Proposal | 2014-03-07 | 2014-03-07 00:05 | 0.083333
Preliminary Research/Proposal | 2014-03-08 08:13 | 2014-03-08 08:17 | 0.069167
Preliminary Research/Proposal | 2014-03-08 08:27 | 2014-03-08 08:36 | 0.15222
Preliminary Research/Proposal | 2014-03-08 13:15 | 2014-03-08 14:47 | 1.5289
Preliminary Research/Proposal | 2014-03-08 15:18 | 2014-03-08 15:53 | 0.58139
Preliminary Research/Proposal | 2014-03-08 15:55 | 2014-03-08 16:12 | 0.28111
Preliminary Research/Proposal | 2014-03-08 16:12 | 2014-03-08 16:12 | 0.0094444
Preliminary Research/Proposal | 2014-03-08 16:24 | 2014-03-08 17:15 | 0.85167
Preliminary Research/Proposal | 2014-03-08 17:26 | 2014-03-08 18:17 | 0.86556
Preliminary Research/Proposal | 2014-03-08 20:50 | 2014-03-08 22:04 | 1.2253
Preliminary Research/Proposal | 2014-03-10 19:38 | 2014-03-10 19:42 | 0.069167
Preliminary Research/Proposal | 2014-03-10 20:00 | 2014-03-10 20:54 | 0.90611
Preliminary Research/Proposal | 2014-03-10 21:01 | 2014-03-10 21:20 | 0.31139
Preliminary Research/Proposal | 2014-03-10 21:20 | 2014-03-10 21:24 | 0.058889
Preliminary Research/Proposal | 2014-03-11 18:15 | 2014-03-11 18:42 | 0.44472
Preliminary Research/Proposal | 2014-03-11 18:42 | 2014-03-11 19:43 | 1.0147
Preliminary Research/Proposal | 2014-03-11 19:50 | 2014-03-11 20:33 | 0.71194
Research | 2014-03-12 19:03 | 2014-03-12 19:30 | 0.44583
Research | 2014-03-12 19:32 | 2014-03-12 19:37 | 0.095
Research | 2014-03-12 19:37 | 2014-03-12 20:22 | 0.73583
Research | 2014-03-12 20:50 | 2014-03-12 21:40 | 0.83417
Research | 2014-03-13 18:38 | 2014-03-13 19:22 | 0.74222
Research | 2014-03-13 21:19 | 2014-03-13 21:21 | 0.027222
Research | 2014-03-15 12:22 | 2014-03-15 13:45 | 1.3831
Research | 2014-03-15 13:52 | 2014-03-15 15:10 | 1.3081
Research | 2014-03-15 15:23 | 2014-03-15 16:53 | 1.5011
Research | 2014-03-15 16:55 | 2014-03-15 17:18 | 0.37389
Requirements | 2014-03-15 17:18 | 2014-03-15 17:29 | 0.18806
Research | 2014-03-15 17:30 | 2014-03-15 17:32 | 0.03
Requirements | 2014-03-15 17:32 | 2014-03-15 17:58 | 0.42556
Research | 2014-03-15 17:58 | 2014-03-15 17:58 | 0.0022222
Research | 2014-03-17 18:59 | 2014-03-17 19:07 | 0.13028
Research | 2014-03-17 19:12 | 2014-03-17 19:23 | 0.17611
Requirements | 2014-03-17 19:23 | 2014-03-17 19:34 | 0.18306
Research | 2014-03-17 19:34 | 2014-03-17 19:48 | 0.22333
Research | 2014-03-17 19:54 | 2014-03-17 20:03 | 0.14361
Research | 2014-03-17 20:18 | 2014-03-17 20:35 | 0.27528
Requirements | 2014-03-17 20:37 | 2014-03-17 20:41 | 0.075
Requirements | 2014-03-17 20:44 | 2014-03-17 20:52 | 0.12194
Requirements | 2014-03-17 20:54 | 2014-03-17 21:23 | 0.48389
Research | 2014-03-17 21:24 | 2014-03-17 21:35 | 0.19528
Research | 2014-03-18 18:11 | 2014-03-18 18:42 | 0.52167
Research | 2014-03-18 18:44 | 2014-03-18 19:08 | 0.39694
Research | 2014-03-18 19:09 | 2014-03-18 19:33 | 0.39222
Research | 2014-03-18 19:35 | 2014-03-18 19:35 | 0.0019444
Research | 2014-03-18 19:42 | 2014-03-18 19:48 | 0.097222
Research | 2014-03-18 20:26 | 2014-03-18 21:31 | 1.0758
Research | 2014-03-19 18:47 | 2014-03-19 18:53 | 0.0975
Research | 2014-03-19 18:55 | 2014-03-19 18:57 | 0.043056
Research | 2014-03-19 19:12 | 2014-03-19 19:37 | 0.425
Research | 2014-03-19 19:50 | 2014-03-19 21:35 | 1.7408
Requirements | 2014-03-19 21:35 | 2014-03-19 21:40 | 0.0825
Requirements | 2014-03-19 21:40 | 2014-03-19 21:48 | 0.13028
Research | 2014-03-19 21:49 | 2014-03-19 21:49 | 0.0030556
Research | 2014-03-20 19:45 | 2014-03-20 20:18 | 0.55
Requirements | 2014-03-20 20:19 | 2014-03-20 21:32 | 1.2225
Requirements | 2014-03-22 15:28 | 2014-03-22 15:31 | 0.053611
Research | 2014-03-22 15:31 | 2014-03-22 17:10 | 1.6544
Research | 2014-03-22 17:22 | 2014-03-22 18:20 | 0.97111
Research | 2014-03-22 18:21 | 2014-03-22 18:22 | 0.023611
Research | 2014-03-22 18:28 | 2014-03-22 18:52 | 0.40611
Research | 2014-03-22 19:31 | 2014-03-22 19:46 | 0.2625
Research | 2014-03-22 20:39 | 2014-03-22 21:24 | 0.74778
Requirements | 2014-03-24 20:01 | 2014-03-24 20:01 | 0.010833
Requirements | 2014-03-24 20:06 | 2014-03-24 20:17 | 0.18389
Requirements | 2014-03-24 20:22 | 2014-03-24 20:23 | 0.018611
Research | 2014-03-25 18:44 | 2014-03-25 18:46 | 0.031111
Research | 2014-03-25 18:46 | 2014-03-25 20:07 | 1.3394
Requirements | 2014-03-25 20:07 | 2014-03-25 20:13 | 0.10778
Requirements | 2014-03-25 20:36 | 2014-03-25 20:41 | 0.080833
Requirements | 2014-03-25 21:24 | 2014-03-25 21:50 | 0.42889
Design | 2014-03-25 21:50 | 2014-03-25 21:53 | 0.053056
Design | 2014-03-26 18:30 | 2014-03-26 18:31 | 0.018056
Design | 2014-03-26 18:33 | 2014-03-26 18:54 | 0.34444
Research | 2014-03-26 18:54 | 2014-03-26 19:08 | 0.23944
Research | 2014-03-26 19:10 | 2014-03-26 19:37 | 0.45278
Design | 2014-03-26 19:37 | 2014-03-26 20:21 | 0.72861
Design | 2014-03-26 20:49 | 2014-03-26 21:24 | 0.58444
Research | 2014-03-28 05:46 | 2014-03-28 06:07 | 0.36417
Design | 2014-03-28 06:07 | 2014-03-28 06:32 | 0.40611
Design | 2014-03-28 12:44 | 2014-03-28 12:49 | 0.077778
Research | 2014-03-28 12:49 | 2014-03-28 13:18 | 0.48639
Research | 2014-03-28 13:25 | 2014-03-28 13:57 | 0.51861
Design | 2014-03-29 13:23 | 2014-03-29 14:04 | 0.67889
Design | 2014-03-29 14:53 | 2014-03-29 15:46 | 0.87667
Design | 2014-03-29 16:02 | 2014-03-29 16:15 | 0.22472
Design | 2014-03-31 10:11 | 2014-03-31 12:14 | 2.0503
Design | 2014-04-01 18:22 | 2014-04-01 19:33 | 1.1833
Design | 2014-04-01 19:37 | 2014-04-01 20:01 | 0.40278
Design | 2014-04-01 20:05 | 2014-04-01 20:24 | 0.325
Research | 2014-04-01 20:24 | 2014-04-01 20:28 | 0.056667
Research | 2014-04-01 21:00 | 2014-04-01 21:18 | 0.29278
Math Unit Test and code | 2014-04-01 21:18 | 2014-04-01 21:25 | 0.11833
Sequential Ray Tracer Tests and code | 2014-04-01 21:25 | 2014-04-01 21:49 | 0.40111
Design | 2014-04-02 18:00 | 2014-04-02 18:02 | 0.039167
Research | 2014-04-02 18:02 | 2014-04-02 18:08 | 0.10056
Sequential Ray Tracer Tests and code | 2014-04-02 18:08 | 2014-04-02 18:42 | 0.5625
Research | 2014-04-02 18:42 | 2014-04-02 19:19 | 0.62333
Design | 2014-04-02 19:19 | 2014-04-02 19:28 | 0.14944
Sequential Ray Tracer Tests and code | 2014-04-02 19:28 | 2014-04-02 19:54 | 0.42639
Sequential Ray Tracer Tests and code | 2014-04-02 19:59 | 2014-04-02 20:20 | 0.34472
Sequential Ray Tracer Tests and code | 2014-04-02 20:49 | 2014-04-02 21:25 | 0.60583
Design | 2014-04-02 21:25 | 2014-04-02 21:33 | 0.12944
Research | 2014-04-02 21:33 | 2014-04-02 21:57 | 0.39167
Sequential Ray Tracer Tests and code | 2014-04-05 12:05 | 2014-04-05 12:10 | 0.083611
Math Unit Test and code | 2014-04-05 12:10 | 2014-04-05 12:30 | 0.33944
Sequential Ray Tracer Tests and code | 2014-04-05 12:30 | 2014-04-05 13:08 | 0.62778
Research | 2014-04-05 13:08 | 2014-04-05 14:01 | 0.88972
Sequential Ray Tracer Tests and code | 2014-04-05 14:01 | 2014-04-05 14:06 | 0.081389
Sequential Ray Tracer Tests and code | 2014-04-05 14:07 | 2014-04-05 14:36 | 0.49306
Sequential Ray Tracer Tests and code | 2014-04-05 14:37 | 2014-04-05 14:47 | 0.16972
Sequential Ray Tracer Tests and code | 2014-04-05 14:50 | 2014-04-05 15:10 | 0.31778
Sequential Ray Tracer Tests and code | 2014-04-05 15:11 | 2014-04-05 15:46 | 0.59639
Sequential Ray Tracer Tests and code | 2014-04-05 15:54 | 2014-04-05 16:27 | 0.53472
Sequential Ray Tracer Tests and code | 2014-04-05 16:38 | 2014-04-05 16:49 | 0.19194
Sequential Ray Tracer Tests and code | 2014-04-07 21:32 | 2014-04-07 21:41 | 0.145
Sequential Ray Tracer Tests and code | 2014-04-08 18:37 | 2014-04-08 18:37 | 0.0036111
Research | 2014-04-08 18:37 | 2014-04-08 19:03 | 0.43222
Research | 2014-04-08 19:07 | 2014-04-08 20:38 | 1.5217
Math Unit Test and code | 2014-04-08 20:38 | 2014-04-08 20:40 | 0.0325
Math Unit Test and code | 2014-04-08 21:08 | 2014-04-08 21:09 | 0.017222
Math Unit Test and code | 2014-04-08 21:11 | 2014-04-08 22:07 | 0.91944
Math Unit Test and code | 2014-04-09 18:03 | 2014-04-09 19:10 | 1.1222
Research | 2014-04-09 19:10 | 2014-04-09 20:12 | 1.0303
Math Unit Test and code | 2014-04-09 20:15 | 2014-04-09 21:05 | 0.84583