## Report
Michael Warren | [10 empty] | Last Report Date
Task | Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours |  |  | 2014-03-20
|  | Proposed | Modified | Actual | Proposed | Modified | Actual | Proposed | Modified | Actual
Preliminary Research/Proposal | Completed | 2014-03-06 |  | 2014-03-06 | 2014-03-13 |  | 2014-03-12 | 12 |  | 14.165
Research | In Progress | 2014-03-13 |  | 2014-03-12 | 2014-03-31 |  |  | 30 |  | 16.5933
Requirements | in Progress | 2014-03-31 |  | 2014-03-15 | 2014-04-04 |  |  | 6 |  | 2.9664
Design | Not Started | 2014-04-04 |  |  | 2014-04-11 |  |  | 12 |  | 0
Math Unit Test and code | Not Started | 2014-04-11 |  |  | 2014-04-24 |  |  | 18 |  | 0
Sequential Ray Tracer Tests and code | Not Started | 2014-04-24 |  |  | 2014-05-05 |  |  | 18 |  | 0
Parallel Ray Tracer Code | Not Started | 2014-05-05 |  |  | 2014-05-15 |  |  | 18 |  | 0
Cluster Ray Tracer Code | Not Started | 2014-05-15 |  |  | 2014-06-09 |  |  | 42 |  | 0
Total Hours | --- | --- | --- | --- | --- | --- | --- | 156 |  | 33.7247
Accomplishments: Lots of reasearch done already. Requierments are started as well.
Problems: Baby not letting me or my wife sleep as much as we want.
Changes in Scope, Schedule, and Cost:
Confessional
Actual hours since last update: | 4.4517
Total anticipated actual hours: | 156
Ahead by 3 hours
Scripture " 15 For behold, we are in bondage to the [senior project] and are taxed with a tax which is grievous to be borne..." - Mosiah 7:15 "12 But I was racked with eternal torment, for my soul was harrowed up to the greatest degree and racked with all my sins. " Alma 36:12

## Time
Preliminary Research/Proposal | 2014-03-05 | 2014-03-05 02:00 | 2
Preliminary Research/Proposal | 2014-03-06 | 2014-03-06 03:00 | 3
Preliminary Research/Proposal | 2014-03-07 | 2014-03-07 00:05 | 0.083333
Preliminary Research/Proposal | 2014-03-08 08:13 | 2014-03-08 08:17 | 0.069167
Preliminary Research/Proposal | 2014-03-08 08:27 | 2014-03-08 08:36 | 0.15222
Preliminary Research/Proposal | 2014-03-08 13:15 | 2014-03-08 14:47 | 1.5289
Preliminary Research/Proposal | 2014-03-08 15:18 | 2014-03-08 15:53 | 0.58139
Preliminary Research/Proposal | 2014-03-08 15:55 | 2014-03-08 16:12 | 0.28111
Preliminary Research/Proposal | 2014-03-08 16:12 | 2014-03-08 16:12 | 0.0094444
Preliminary Research/Proposal | 2014-03-08 16:24 | 2014-03-08 17:15 | 0.85167
Preliminary Research/Proposal | 2014-03-08 17:26 | 2014-03-08 18:17 | 0.86556
Preliminary Research/Proposal | 2014-03-08 20:50 | 2014-03-08 22:04 | 1.2253
Preliminary Research/Proposal | 2014-03-10 19:38 | 2014-03-10 19:42 | 0.069167
Preliminary Research/Proposal | 2014-03-10 20:00 | 2014-03-10 20:54 | 0.90611
Preliminary Research/Proposal | 2014-03-10 21:01 | 2014-03-10 21:20 | 0.31139
Preliminary Research/Proposal | 2014-03-10 21:20 | 2014-03-10 21:24 | 0.058889
Preliminary Research/Proposal | 2014-03-11 18:15 | 2014-03-11 18:42 | 0.44472
Preliminary Research/Proposal | 2014-03-11 18:42 | 2014-03-11 19:43 | 1.0147
Preliminary Research/Proposal | 2014-03-11 19:50 | 2014-03-11 20:33 | 0.71194
Research | 2014-03-12 19:03 | 2014-03-12 19:30 | 0.44583
Research | 2014-03-12 19:32 | 2014-03-12 19:37 | 0.095
Research | 2014-03-12 19:37 | 2014-03-12 20:22 | 0.73583
Research | 2014-03-12 20:50 | 2014-03-12 21:40 | 0.83417
Research | 2014-03-13 18:38 | 2014-03-13 19:22 | 0.74222
Research | 2014-03-13 21:19 | 2014-03-13 21:21 | 0.027222
Research | 2014-03-15 12:22 | 2014-03-15 13:45 | 1.3831
Research | 2014-03-15 13:52 | 2014-03-15 15:10 | 1.3081
Research | 2014-03-15 15:23 | 2014-03-15 16:53 | 1.5011
Research | 2014-03-15 16:55 | 2014-03-15 17:18 | 0.37389
Requirements | 2014-03-15 17:18 | 2014-03-15 17:29 | 0.18806
Research | 2014-03-15 17:30 | 2014-03-15 17:32 | 0.03
Requirements | 2014-03-15 17:32 | 2014-03-15 17:58 | 0.42556
Research | 2014-03-15 17:58 | 2014-03-15 17:58 | 0.0022222
Research | 2014-03-17 18:59 | 2014-03-17 19:07 | 0.13028
Research | 2014-03-17 19:12 | 2014-03-17 19:23 | 0.17611
Requirements | 2014-03-17 19:23 | 2014-03-17 19:34 | 0.18306
Research | 2014-03-17 19:34 | 2014-03-17 19:48 | 0.22333
Research | 2014-03-17 19:54 | 2014-03-17 20:03 | 0.14361
Research | 2014-03-17 20:18 | 2014-03-17 20:35 | 0.27528
Requirements | 2014-03-17 20:37 | 2014-03-17 20:41 | 0.075
Requirements | 2014-03-17 20:44 | 2014-03-17 20:52 | 0.12194
Requirements | 2014-03-17 20:54 | 2014-03-17 21:23 | 0.48389
Research | 2014-03-17 21:24 | 2014-03-17 21:35 | 0.19528
Research | 2014-03-18 18:11 | 2014-03-18 18:42 | 0.52167
Research | 2014-03-18 18:44 | 2014-03-18 19:08 | 0.39694
Research | 2014-03-18 19:09 | 2014-03-18 19:33 | 0.39222
Research | 2014-03-18 19:35 | 2014-03-18 19:35 | 0.0019444
Research | 2014-03-18 19:42 | 2014-03-18 19:48 | 0.097222
Research | 2014-03-18 20:26 | 2014-03-18 21:31 | 1.0758
Research | 2014-03-19 18:47 | 2014-03-19 18:53 | 0.0975
Research | 2014-03-19 18:55 | 2014-03-19 18:57 | 0.043056
Research | 2014-03-19 19:12 | 2014-03-19 19:37 | 0.425
Research | 2014-03-19 19:50 | 2014-03-19 21:35 | 1.7408
Requirements | 2014-03-19 21:35 | 2014-03-19 21:40 | 0.0825
Requirements | 2014-03-19 21:40 | 2014-03-19 21:48 | 0.13028
Research | 2014-03-19 21:49 | 2014-03-19 21:49 | 0.0030556
Research | 2014-03-20 19:45 | 2014-03-20 20:18 | 0.55
Requirements | 2014-03-20 20:19 | 2014-03-20 21:32 | 1.2225
Requirements | 2014-03-22 15:28 | 2014-03-22 15:31 | 0.053611
Research | 2014-03-22 15:31 | 2014-03-22 17:10 | 1.6544
Research | 2014-03-22 17:22 | 2014-03-22 18:20 | 0.97111
Research | 2014-03-22 18:21 |  | 0