## Report
Michael Warren | [10 empty] | Last Report Date | Report as of
Task | Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours |  |  | 2014-04-16 21:29 | 2014-04-24 18:57
|  | Proposed | Modified | Actual | Proposed | Modified | Actual | Proposed | Modified | Actual
Preliminary Research/Proposal | Completed | 2014-03-06 |  | 2014-03-06 | 2014-03-13 |  | 2014-03-12 | 12 |  | 14.165
Research | Completed | 2014-03-13 |  | 2014-03-12 | 2014-03-31 |  | 2014-04-16 | 30 |  | 27.4553
Requirements | Completed | 2014-03-31 |  | 2014-03-15 | 2014-04-04 |  | 2014-03-26 | 6 |  | 3.7972
Design | Completed | 2014-04-04 |  | 2014-03-26 | 2014-04-11 |  | 2014-04-09 | 12 |  | 8.2722
Math Unit Test and code | Completed | 2014-04-11 |  | 2014-04-01 | 2014-04-24 |  | 2014-04-24 | 18 |  | 9.8056
Sequential Ray Tracer Tests and code | In Progress | 2014-04-24 |  | 2014-04-01 | 2014-05-05 |  |  | 18 |  | 18.5272
Parallel Ray Tracer Code | Not Started | 2014-05-05 |  |  | 2014-05-15 |  |  | 18 |  | 0
Cluster Ray Tracer Code | Not Started | 2014-05-15 |  |  | 2014-06-09 |  |  | 42 |  | 0
Total Hours | --- | --- | --- | --- | --- | --- | --- | 156 |  | 82.0225
Accomplishments: I can draw flat boxes and spheres (they don't look 3d yet) drawing to a close for the sequential ray tracing. Finished math section kind of there is a blurry line for math and sequentail ray tracer.
Problems: Inlaws are in town and sick and tire of traveling my self.
Changes in Scope, Schedule, and Cost:
Confessional
Actual hours since last update: | 10.6658
Total anticipated actual hours: | 156
On Schedule
Scripture " 15 For behold, we are in bondage to the [senior project] and are taxed with a tax which is grievous to be borne..." - Mosiah 7:15 " 20 ¶And it came to pass the third day, which was Pharaoh’s birthday, that he made a feast unto all his servants: and he lifted up the head of the chief butler and of the chief baker among his servants. 21 And he restored the chief butler unto his butlership again; and he gave the cup into Pharaoh’s hand:" Genisis 40:20-21

## Time
Preliminary Research/Proposal | 2014-03-05 | 2014-03-05 02:00 | 2
Preliminary Research/Proposal | 2014-03-06 | 2014-03-06 03:00 | 3
Preliminary Research/Proposal | 2014-03-07 | 2014-03-07 00:05 | 0.083333
Preliminary Research/Proposal | 2014-03-08 08:13 | 2014-03-08 08:17 | 0.069167
Preliminary Research/Proposal | 2014-03-08 08:27 | 2014-03-08 08:36 | 0.15222
Preliminary Research/Proposal | 2014-03-08 13:15 | 2014-03-08 14:47 | 1.5289
Preliminary Research/Proposal | 2014-03-08 15:18 | 2014-03-08 15:53 | 0.58139
Preliminary Research/Proposal | 2014-03-08 15:55 | 2014-03-08 16:12 | 0.28111
Preliminary Research/Proposal | 2014-03-08 16:12 | 2014-03-08 16:12 | 0.0094444
Preliminary Research/Proposal | 2014-03-08 16:24 | 2014-03-08 17:15 | 0.85167
Preliminary Research/Proposal | 2014-03-08 17:26 | 2014-03-08 18:17 | 0.86556
Preliminary Research/Proposal | 2014-03-08 20:50 | 2014-03-08 22:04 | 1.2253
Preliminary Research/Proposal | 2014-03-10 19:38 | 2014-03-10 19:42 | 0.069167
Preliminary Research/Proposal | 2014-03-10 20:00 | 2014-03-10 20:54 | 0.90611
Preliminary Research/Proposal | 2014-03-10 21:01 | 2014-03-10 21:20 | 0.31139
Preliminary Research/Proposal | 2014-03-10 21:20 | 2014-03-10 21:24 | 0.058889
Preliminary Research/Proposal | 2014-03-11 18:15 | 2014-03-11 18:42 | 0.44472
Preliminary Research/Proposal | 2014-03-11 18:42 | 2014-03-11 19:43 | 1.0147
Preliminary Research/Proposal | 2014-03-11 19:50 | 2014-03-11 20:33 | 0.71194
Research | 2014-03-12 19:03 | 2014-03-12 19:30 | 0.44583
Research | 2014-03-12 19:32 | 2014-03-12 19:37 | 0.095
Research | 2014-03-12 19:37 | 2014-03-12 20:22 | 0.73583
Research | 2014-03-12 20:50 | 2014-03-12 21:40 | 0.83417
Research | 2014-03-13 18:38 | 2014-03-13 19:22 | 0.74222
Research | 2014-03-13 21:19 | 2014-03-13 21:21 | 0.027222
Research | 2014-03-15 12:22 | 2014-03-15 13:45 | 1.3831
Research | 2014-03-15 13:52 | 2014-03-15 15:10 | 1.3081
Research | 2014-03-15 15:23 | 2014-03-15 16:53 | 1.5011
Research | 2014-03-15 16:55 | 2014-03-15 17:18 | 0.37389
Requirements | 2014-03-15 17:18 | 2014-03-15 17:29 | 0.18806
Research | 2014-03-15 17:30 | 2014-03-15 17:32 | 0.03
Requirements | 2014-03-15 17:32 | 2014-03-15 17:58 | 0.42556
Research | 2014-03-15 17:58 | 2014-03-15 17:58 | 0.0022222
Research | 2014-03-17 18:59 | 2014-03-17 19:07 | 0.13028
Research | 2014-03-17 19:12 | 2014-03-17 19:23 | 0.17611
Requirements | 2014-03-17 19:23 | 2014-03-17 19:34 | 0.18306
Research | 2014-03-17 19:34 | 2014-03-17 19:48 | 0.22333
Research | 2014-03-17 19:54 | 2014-03-17 20:03 | 0.14361
Research | 2014-03-17 20:18 | 2014-03-17 20:35 | 0.27528
Requirements | 2014-03-17 20:37 | 2014-03-17 20:41 | 0.075
Requirements | 2014-03-17 20:44 | 2014-03-17 20:52 | 0.12194
Requirements | 2014-03-17 20:54 | 2014-03-17 21:23 | 0.48389
Research | 2014-03-17 21:24 | 2014-03-17 21:35 | 0.19528
Research | 2014-03-18 18:11 | 2014-03-18 18:42 | 0.52167
Research | 2014-03-18 18:44 | 2014-03-18 19:08 | 0.39694
Research | 2014-03-18 19:09 | 2014-03-18 19:33 | 0.39222
Research | 2014-03-18 19:35 | 2014-03-18 19:35 | 0.0019444
Research | 2014-03-18 19:42 | 2014-03-18 19:48 | 0.097222
Research | 2014-03-18 20:26 | 2014-03-18 21:31 | 1.0758
Research | 2014-03-19 18:47 | 2014-03-19 18:53 | 0.0975
Research | 2014-03-19 18:55 | 2014-03-19 18:57 | 0.043056
Research | 2014-03-19 19:12 | 2014-03-19 19:37 | 0.425
Research | 2014-03-19 19:50 | 2014-03-19 21:35 | 1.7408
Requirements | 2014-03-19 21:35 | 2014-03-19 21:40 | 0.0825
Requirements | 2014-03-19 21:40 | 2014-03-19 21:48 | 0.13028
Research | 2014-03-19 21:49 | 2014-03-19 21:49 | 0.0030556
Research | 2014-03-20 19:45 | 2014-03-20 20:18 | 0.55
Requirements | 2014-03-20 20:19 | 2014-03-20 21:32 | 1.2225
Requirements | 2014-03-22 15:28 | 2014-03-22 15:31 | 0.053611
Research | 2014-03-22 15:31 | 2014-03-22 17:10 | 1.6544
Research | 2014-03-22 17:22 | 2014-03-22 18:20 | 0.97111
Research | 2014-03-22 18:21 | 2014-03-22 18:22 | 0.023611
Research | 2014-03-22 18:28 | 2014-03-22 18:52 | 0.40611
Research | 2014-03-22 19:31 | 2014-03-22 19:46 | 0.2625
Research | 2014-03-22 20:39 | 2014-03-22 21:24 | 0.74778
Requirements | 2014-03-24 20:01 | 2014-03-24 20:01 | 0.010833
Requirements | 2014-03-24 20:06 | 2014-03-24 20:17 | 0.18389
Requirements | 2014-03-24 20:22 | 2014-03-24 20:23 | 0.018611
Research | 2014-03-25 18:44 | 2014-03-25 18:46 | 0.031111
Research | 2014-03-25 18:46 | 2014-03-25 20:07 | 1.3394
Requirements | 2014-03-25 20:07 | 2014-03-25 20:13 | 0.10778
Requirements | 2014-03-25 20:36 | 2014-03-25 20:41 | 0.080833
Requirements | 2014-03-25 21:24 | 2014-03-25 21:50 | 0.42889
Design | 2014-03-25 21:50 | 2014-03-25 21:53 | 0.053056
Design | 2014-03-26 18:30 | 2014-03-26 18:31 | 0.018056
Design | 2014-03-26 18:33 | 2014-03-26 18:54 | 0.34444
Research | 2014-03-26 18:54 | 2014-03-26 19:08 | 0.23944
Research | 2014-03-26 19:10 | 2014-03-26 19:37 | 0.45278
Design | 2014-03-26 19:37 | 2014-03-26 20:21 | 0.72861
Design | 2014-03-26 20:49 | 2014-03-26 21:24 | 0.58444
Research | 2014-03-28 05:46 | 2014-03-28 06:07 | 0.36417
Design | 2014-03-28 06:07 | 2014-03-28 06:32 | 0.40611
Design | 2014-03-28 12:44 | 2014-03-28 12:49 | 0.077778
Research | 2014-03-28 12:49 | 2014-03-28 13:18 | 0.48639
Research | 2014-03-28 13:25 | 2014-03-28 13:57 | 0.51861
Design | 2014-03-29 13:23 | 2014-03-29 14:04 | 0.67889
Design | 2014-03-29 14:53 | 2014-03-29 15:46 | 0.87667
Design | 2014-03-29 16:02 | 2014-03-29 16:15 | 0.22472
Design | 2014-03-31 10:11 | 2014-03-31 12:14 | 2.0503
Design | 2014-04-01 18:22 | 2014-04-01 19:33 | 1.1833
Design | 2014-04-01 19:37 | 2014-04-01 20:01 | 0.40278
Design | 2014-04-01 20:05 | 2014-04-01 20:24 | 0.325
Research | 2014-04-01 20:24 | 2014-04-01 20:28 | 0.056667
Research | 2014-04-01 21:00 | 2014-04-01 21:18 | 0.29278
Math Unit Test and code | 2014-04-01 21:18 | 2014-04-01 21:25 | 0.11833
Sequential Ray Tracer Tests and code | 2014-04-01 21:25 | 2014-04-01 21:49 | 0.40111
Design | 2014-04-02 18:00 | 2014-04-02 18:02 | 0.039167
Research | 2014-04-02 18:02 | 2014-04-02 18:08 | 0.10056
Sequential Ray Tracer Tests and code | 2014-04-02 18:08 | 2014-04-02 18:42 | 0.5625
Research | 2014-04-02 18:42 | 2014-04-02 19:19 | 0.62333
Design | 2014-04-02 19:19 | 2014-04-02 19:28 | 0.14944
Sequential Ray Tracer Tests and code | 2014-04-02 19:28 | 2014-04-02 19:54 | 0.42639
Sequential Ray Tracer Tests and code | 2014-04-02 19:59 | 2014-04-02 20:20 | 0.34472
Sequential Ray Tracer Tests and code | 2014-04-02 20:49 | 2014-04-02 21:25 | 0.60583
Design | 2014-04-02 21:25 | 2014-04-02 21:33 | 0.12944
Research | 2014-04-02 21:33 | 2014-04-02 21:57 | 0.39167
Sequential Ray Tracer Tests and code | 2014-04-05 12:05 | 2014-04-05 12:10 | 0.083611
Math Unit Test and code | 2014-04-05 12:10 | 2014-04-05 12:30 | 0.33944
Sequential Ray Tracer Tests and code | 2014-04-05 12:30 | 2014-04-05 13:08 | 0.62778
Research | 2014-04-05 13:08 | 2014-04-05 14:01 | 0.88972
Sequential Ray Tracer Tests and code | 2014-04-05 14:01 | 2014-04-05 14:06 | 0.081389
Sequential Ray Tracer Tests and code | 2014-04-05 14:07 | 2014-04-05 14:36 | 0.49306
Sequential Ray Tracer Tests and code | 2014-04-05 14:37 | 2014-04-05 14:47 | 0.16972
Sequential Ray Tracer Tests and code | 2014-04-05 14:50 | 2014-04-05 15:10 | 0.31778
Sequential Ray Tracer Tests and code | 2014-04-05 15:11 | 2014-04-05 15:46 | 0.59639
Sequential Ray Tracer Tests and code | 2014-04-05 15:54 | 2014-04-05 16:27 | 0.53472
Sequential Ray Tracer Tests and code | 2014-04-05 16:38 | 2014-04-05 16:49 | 0.19194
Sequential Ray Tracer Tests and code | 2014-04-07 21:32 | 2014-04-07 21:41 | 0.145
Sequential Ray Tracer Tests and code | 2014-04-08 18:37 | 2014-04-08 18:37 | 0.0036111
Research | 2014-04-08 18:37 | 2014-04-08 19:03 | 0.43222
Research | 2014-04-08 19:07 | 2014-04-08 20:38 | 1.5217
Math Unit Test and code | 2014-04-08 20:38 | 2014-04-08 20:40 | 0.0325
Math Unit Test and code | 2014-04-08 21:08 | 2014-04-08 21:09 | 0.017222
Math Unit Test and code | 2014-04-08 21:11 | 2014-04-08 22:07 | 0.91944
Math Unit Test and code | 2014-04-09 18:03 | 2014-04-09 19:10 | 1.1222
Research | 2014-04-09 19:10 | 2014-04-09 20:12 | 1.0303
Math Unit Test and code | 2014-04-09 20:15 | 2014-04-09 21:05 | 0.84583
Math Unit Test and code | 2014-04-09 21:06 | 2014-04-09 21:27 | 0.35083
Sequential Ray Tracer Tests and code | 2014-04-10 19:10 | 2014-04-10 19:49 | 0.65583
Sequential Ray Tracer Tests and code | 2014-04-10 20:35 | 2014-04-10 22:10 | 1.5703
Sequential Ray Tracer Tests and code | 2014-04-15 18:10 | 2014-04-15 18:22 | 0.19417
Sequential Ray Tracer Tests and code | 2014-04-15 18:26 | 2014-04-15 18:34 | 0.12361
Math Unit Test and code | 2014-04-15 18:34 | 2014-04-15 20:04 | 1.5022
Sequential Ray Tracer Tests and code | 2014-04-15 20:11 | 2014-04-15 21:14 | 1.0539
Math Unit Test and code | 2014-04-15 21:14 | 2014-04-15 21:14 | 0.0038889
Research | 2014-04-15 21:14 | 2014-04-15 21:53 | 0.65111
Sequential Ray Tracer Tests and code | 2014-04-15 21:53 | 2014-04-15 22:07 | 0.23306
Sequential Ray Tracer Tests and code | 2014-04-16 18:19 | 2014-04-16 20:25 | 2.0997
Sequential Ray Tracer Tests and code | 2014-04-16 20:35 | 2014-04-16 21:29 | 0.89889
Sequential Ray Tracer Tests and code | 2014-04-16 21:29 | 2014-04-16 21:59 | 0.50444
Sequential Ray Tracer Tests and code | 2014-04-19 08:56 | 2014-04-19 09:29 | 0.55194
Math Unit Test and code | 2014-04-19 09:29 | 2014-04-19 09:55 | 0.43944
Math Unit Test and code | 2014-04-19 19:54 | 2014-04-19 21:13 | 1.3183
Math Unit Test and code | 2014-04-21 20:12 | 2014-04-21 21:42 | 1.4956
Sequential Ray Tracer Tests and code | 2014-04-22 17:39 | 2014-04-22 18:41 | 1.0422
Sequential Ray Tracer Tests and code | 2014-04-22 19:29 | 2014-04-22 19:50 | 0.36167
Sequential Ray Tracer Tests and code | 2014-04-22 19:56 | 2014-04-22 20:16 | 0.34667
Sequential Ray Tracer Tests and code | 2014-04-22 20:20 | 2014-04-22 20:57 | 0.61222
Sequential Ray Tracer Tests and code | 2014-04-22 21:28 | 2014-04-22 22:23 | 0.92889
Sequential Ray Tracer Tests and code | 2014-04-23 17:34 | 2014-04-23 17:46 | 0.19472
Sequential Ray Tracer Tests and code | 2014-04-23 18:02 | 2014-04-23 18:28 | 0.42722
Sequential Ray Tracer Tests and code | 2014-04-23 19:08 | 2014-04-23 19:36 | 0.46806
Sequential Ray Tracer Tests and code | 2014-04-23 20:06 | 2014-04-23 20:24 | 0.30722
Sequential Ray Tracer Tests and code | 2014-04-23 20:32 | 2014-04-23 20:54 | 0.36694
Math Unit Test and code | 2014-04-23 20:54 | 2014-04-23 20:58 | 0.064444
Math Unit Test and code | 2014-04-23 20:58 | 2014-04-23 22:12 | 1.2261
Math Unit Test and code | 2014-04-24 18:57 | 2014-04-24 18:57 | 0.0097222