## Report
Michael Warren | [10 empty] | Last Report Date
Task | Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours |  |  | 2014-03-04
|  | Proposed | Modified | Actual | Proposed | Modified | Actual | Proposed | Modified | Actual
Preliminary Research/Proposal | Completed | 2014-03-06 |  | 2014-03-06 | 2014-03-13 |  | 2014-03-12 | 12 |  | 14.165
Research | In Progress | 2014-03-13 |  | 2014-03-12 | 2014-03-31 |  |  | 30 |  | 2.8803
Requirements | Not Started | 2014-03-31 |  |  | 2014-04-04 |  |  | 6 |  | 0
Design | Not Started | 2014-04-04 |  |  | 2014-04-11 |  |  | 12 |  | 0
Math Unit Test and code | Not Started | 2014-04-11 |  |  | 2014-04-24 |  |  | 18 |  | 0
Sequential Ray Tracer Tests and code | Not Started | 2014-04-24 |  |  | 2014-05-05 |  |  | 18 |  | 0
Parallel Ray Tracer Code | Not Started | 2014-05-05 |  |  | 2014-05-15 |  |  | 18 |  | 0
Cluster Ray Tracer Code | Not Started | 2014-05-15 |  |  | 2014-06-09 |  |  | 42 |  | 0
Total Hours | --- | --- | --- | --- | --- | --- | --- | 156 |  | 17.0453
Accomplishments: Proposal for new project has been accepted
Problems: Had to start a new project.
Changes in Scope, Schedule, and Cost: New project Cluster computing/parallel programming
Confessional
Actual hours since last update: | 17.0453
Total anticipated actual hours: | 156
On schedule
Scripture " 15 For behold, we are in bondage to the [senior project] and are taxed with a tax which is grievous to be borne..." - Mosiah 7:15 " 14 Now I say unto you that ye must repent, and be born again; for the Spirit saith if ye are not born again ye cannot inherit the kingdom of heaven; " Alma 7:14

## Time
Preliminary Research/Proposal | 2014-03-05 | 2014-03-05 02:00 | 2
Preliminary Research/Proposal | 2014-03-06 | 2014-03-06 03:00 | 3
Preliminary Research/Proposal | 2014-03-07 | 2014-03-07 00:05 | 0.083333
Preliminary Research/Proposal | 2014-03-08 08:13 | 2014-03-08 08:17 | 0.069167
Preliminary Research/Proposal | 2014-03-08 08:27 | 2014-03-08 08:36 | 0.15222
Preliminary Research/Proposal | 2014-03-08 13:15 | 2014-03-08 14:47 | 1.5289
Preliminary Research/Proposal | 2014-03-08 15:18 | 2014-03-08 15:53 | 0.58139
Preliminary Research/Proposal | 2014-03-08 15:55 | 2014-03-08 16:12 | 0.28111
Preliminary Research/Proposal | 2014-03-08 16:12 | 2014-03-08 16:12 | 0.0094444
Preliminary Research/Proposal | 2014-03-08 16:24 | 2014-03-08 17:15 | 0.85167
Preliminary Research/Proposal | 2014-03-08 17:26 | 2014-03-08 18:17 | 0.86556
Preliminary Research/Proposal | 2014-03-08 20:50 | 2014-03-08 22:04 | 1.2253
Preliminary Research/Proposal | 2014-03-10 19:38 | 2014-03-10 19:42 | 0.069167
Preliminary Research/Proposal | 2014-03-10 20:00 | 2014-03-10 20:54 | 0.90611
Preliminary Research/Proposal | 2014-03-10 21:01 | 2014-03-10 21:20 | 0.31139
Preliminary Research/Proposal | 2014-03-10 21:20 | 2014-03-10 21:24 | 0.058889
Preliminary Research/Proposal | 2014-03-11 18:15 | 2014-03-11 18:42 | 0.44472
Preliminary Research/Proposal | 2014-03-11 18:42 | 2014-03-11 19:43 | 1.0147
Preliminary Research/Proposal | 2014-03-11 19:50 | 2014-03-11 20:33 | 0.71194
Research | 2014-03-12 19:03 | 2014-03-12 19:30 | 0.44583
Research | 2014-03-12 19:32 | 2014-03-12 19:37 | 0.095
Research | 2014-03-12 19:37 | 2014-03-12 20:22 | 0.73583
Research | 2014-03-12 20:50 | 2014-03-12 21:40 | 0.83417
Research | 2014-03-13 18:38 | 2014-03-13 19:22 | 0.74222
Research | 2014-03-13 21:19 | 2014-03-13 21:21 | 0.027222