## Report
Michael Warren | [10 empty] | Last Report Date
Task | Current Status | Start Date |  |  | Stop Date |  |  | Number of Hours |  |  | 2014-03-20
|  | Proposed | Modified | Actual | Proposed | Modified | Actual | Proposed | Modified | Actual
Preliminary Research/Proposal | Completed | 2014-03-06 |  | 2014-03-06 | 2014-03-13 |  | 2014-03-12 | 12 |  | 14.165
Research | In Progress | 2014-03-13 |  | 2014-03-12 | 2014-03-31 |  |  | 30 |  | 20.0961
Requirements | Completed | 2014-03-31 |  | 2014-03-15 | 2014-04-04 |  | 2014-03-26 | 6 |  | 3.7972
Design | In Progress | 2014-04-04 |  | 2014-03-26 | 2014-04-11 |  |  | 12 |  | 1.7286
Math Unit Test and code | Not Started | 2014-04-11 |  |  | 2014-04-24 |  |  | 18 |  | 0
Sequential Ray Tracer Tests and code | Not Started | 2014-04-24 |  |  | 2014-05-05 |  |  | 18 |  | 0
Parallel Ray Tracer Code | Not Started | 2014-05-05 |  |  | 2014-05-15 |  |  | 18 |  | 0
Cluster Ray Tracer Code | Not Started | 2014-05-15 |  |  | 2014-06-09 |  |  | 42 |  | 0
Total Hours | --- | --- | --- | --- | --- | --- | --- | 156 |  | 39.7869
Accomplishments: Lots of reasearch done already. Requierments are done. Design is started.
Problems: Baby not letting me or my wife sleep as much as we want. Going out of town this weekend. Some more research may be required.
Changes in Scope, Schedule, and Cost:
Confessional
Actual hours since last update: | 10.5139
Total anticipated actual hours: | 156
On schedule for hours
Will try to catch up on some time lost this week so I can be ahead of hours again. (scheduleStatus = min(scheduleHoursStatus, scheduleDateStatus))
Scripture " 15 For behold, we are in bondage to the [senior project] and are taxed with a tax which is grievous to be borne..." - Mosiah 7:15 "The sleep of a labouring man is sweet, whether he eat little or much: but the abundance of the rich will not suffer him to sleep. " Ecclesiastes 5:12

## Time
Preliminary Research/Proposal | 2014-03-05 | 2014-03-05 02:00 | 2
Preliminary Research/Proposal | 2014-03-06 | 2014-03-06 03:00 | 3
Preliminary Research/Proposal | 2014-03-07 | 2014-03-07 00:05 | 0.083333
Preliminary Research/Proposal | 2014-03-08 08:13 | 2014-03-08 08:17 | 0.069167
Preliminary Research/Proposal | 2014-03-08 08:27 | 2014-03-08 08:36 | 0.15222
Preliminary Research/Proposal | 2014-03-08 13:15 | 2014-03-08 14:47 | 1.5289
Preliminary Research/Proposal | 2014-03-08 15:18 | 2014-03-08 15:53 | 0.58139
Preliminary Research/Proposal | 2014-03-08 15:55 | 2014-03-08 16:12 | 0.28111
Preliminary Research/Proposal | 2014-03-08 16:12 | 2014-03-08 16:12 | 0.0094444
Preliminary Research/Proposal | 2014-03-08 16:24 | 2014-03-08 17:15 | 0.85167
Preliminary Research/Proposal | 2014-03-08 17:26 | 2014-03-08 18:17 | 0.86556
Preliminary Research/Proposal | 2014-03-08 20:50 | 2014-03-08 22:04 | 1.2253
Preliminary Research/Proposal | 2014-03-10 19:38 | 2014-03-10 19:42 | 0.069167
Preliminary Research/Proposal | 2014-03-10 20:00 | 2014-03-10 20:54 | 0.90611
Preliminary Research/Proposal | 2014-03-10 21:01 | 2014-03-10 21:20 | 0.31139
Preliminary Research/Proposal | 2014-03-10 21:20 | 2014-03-10 21:24 | 0.058889
Preliminary Research/Proposal | 2014-03-11 18:15 | 2014-03-11 18:42 | 0.44472
Preliminary Research/Proposal | 2014-03-11 18:42 | 2014-03-11 19:43 | 1.0147
Preliminary Research/Proposal | 2014-03-11 19:50 | 2014-03-11 20:33 | 0.71194
Research | 2014-03-12 19:03 | 2014-03-12 19:30 | 0.44583
Research | 2014-03-12 19:32 | 2014-03-12 19:37 | 0.095
Research | 2014-03-12 19:37 | 2014-03-12 20:22 | 0.73583
Research | 2014-03-12 20:50 | 2014-03-12 21:40 | 0.83417
Research | 2014-03-13 18:38 | 2014-03-13 19:22 | 0.74222
Research | 2014-03-13 21:19 | 2014-03-13 21:21 | 0.027222
Research | 2014-03-15 12:22 | 2014-03-15 13:45 | 1.3831
Research | 2014-03-15 13:52 | 2014-03-15 15:10 | 1.3081
Research | 2014-03-15 15:23 | 2014-03-15 16:53 | 1.5011
Research | 2014-03-15 16:55 | 2014-03-15 17:18 | 0.37389
Requirements | 2014-03-15 17:18 | 2014-03-15 17:29 | 0.18806
Research | 2014-03-15 17:30 | 2014-03-15 17:32 | 0.03
Requirements | 2014-03-15 17:32 | 2014-03-15 17:58 | 0.42556
Research | 2014-03-15 17:58 | 2014-03-15 17:58 | 0.0022222
Research | 2014-03-17 18:59 | 2014-03-17 19:07 | 0.13028
Research | 2014-03-17 19:12 | 2014-03-17 19:23 | 0.17611
Requirements | 2014-03-17 19:23 | 2014-03-17 19:34 | 0.18306
Research | 2014-03-17 19:34 | 2014-03-17 19:48 | 0.22333
Research | 2014-03-17 19:54 | 2014-03-17 20:03 | 0.14361
Research | 2014-03-17 20:18 | 2014-03-17 20:35 | 0.27528
Requirements | 2014-03-17 20:37 | 2014-03-17 20:41 | 0.075
Requirements | 2014-03-17 20:44 | 2014-03-17 20:52 | 0.12194
Requirements | 2014-03-17 20:54 | 2014-03-17 21:23 | 0.48389
Research | 2014-03-17 21:24 | 2014-03-17 21:35 | 0.19528
Research | 2014-03-18 18:11 | 2014-03-18 18:42 | 0.52167
Research | 2014-03-18 18:44 | 2014-03-18 19:08 | 0.39694
Research | 2014-03-18 19:09 | 2014-03-18 19:33 | 0.39222
Research | 2014-03-18 19:35 | 2014-03-18 19:35 | 0.0019444
Research | 2014-03-18 19:42 | 2014-03-18 19:48 | 0.097222
Research | 2014-03-18 20:26 | 2014-03-18 21:31 | 1.0758
Research | 2014-03-19 18:47 | 2014-03-19 18:53 | 0.0975
Research | 2014-03-19 18:55 | 2014-03-19 18:57 | 0.043056
Research | 2014-03-19 19:12 | 2014-03-19 19:37 | 0.425
Research | 2014-03-19 19:50 | 2014-03-19 21:35 | 1.7408
Requirements | 2014-03-19 21:35 | 2014-03-19 21:40 | 0.0825
Requirements | 2014-03-19 21:40 | 2014-03-19 21:48 | 0.13028
Research | 2014-03-19 21:49 | 2014-03-19 21:49 | 0.0030556
Research | 2014-03-20 19:45 | 2014-03-20 20:18 | 0.55
Requirements | 2014-03-20 20:19 | 2014-03-20 21:32 | 1.2225
Requirements | 2014-03-22 15:28 | 2014-03-22 15:31 | 0.053611
Research | 2014-03-22 15:31 | 2014-03-22 17:10 | 1.6544
Research | 2014-03-22 17:22 | 2014-03-22 18:20 | 0.97111
Research | 2014-03-22 18:21 | 2014-03-22 18:22 | 0.023611
Research | 2014-03-22 18:28 | 2014-03-22 18:52 | 0.40611
Research | 2014-03-22 19:31 | 2014-03-22 19:46 | 0.2625
Research | 2014-03-22 20:39 | 2014-03-22 21:24 | 0.74778
Requirements | 2014-03-24 20:01 | 2014-03-24 20:01 | 0.010833
Requirements | 2014-03-24 20:06 | 2014-03-24 20:17 | 0.18389
Requirements | 2014-03-24 20:22 | 2014-03-24 20:23 | 0.018611
Research | 2014-03-25 18:44 | 2014-03-25 18:46 | 0.031111
Research | 2014-03-25 18:46 | 2014-03-25 20:07 | 1.3394
Requirements | 2014-03-25 20:07 | 2014-03-25 20:13 | 0.10778
Requirements | 2014-03-25 20:36 | 2014-03-25 20:41 | 0.080833
Requirements | 2014-03-25 21:24 | 2014-03-25 21:50 | 0.42889
Design | 2014-03-25 21:50 | 2014-03-25 21:53 | 0.053056
Design | 2014-03-26 18:30 | 2014-03-26 18:31 | 0.018056
Design | 2014-03-26 18:33 | 2014-03-26 18:54 | 0.34444
Research | 2014-03-26 18:54 | 2014-03-26 19:08 | 0.23944
Research | 2014-03-26 19:10 | 2014-03-26 19:37 | 0.45278
Design | 2014-03-26 19:37 | 2014-03-26 20:21 | 0.72861
Design | 2014-03-26 20:49 | 2014-03-26 21:24 | 0.58444